Example of a Project Charter for a Teenager Project

| Project: Organization of a Skateboard Tournament |  |  |
| --- | --- | --- |
| Stakeholders Skate Club Board, Municipality President, Sponsor Business Owners | Project Manager Giovanni Toccu - +48.123456 giovanni@pm4teens.com | Sponsor (Bold Skate Crew) Jan Kovalski jan@pm4teens.com |
| Background / Project Scope Over the past few years, the local community has seen a significant rise in the number of the number of young skateboard enthusiasts. Skateboarding not only serves as a recreational activity but also fosters community spirit, discipline, and physical fitness. Recognizing the potential to further galvanize this interest and to provide a platform for these young talents, the idea for the Skateboard Tournament emerged. With local parks serving as popular hubs for skateboarders, it's evident there's an unmet need for an organized event where these enthusiasts can showcase their skills, connect with peers, and further the sport's popularity in the community. |  |  |
| Project Goal Organize a skateboard tournament at the local park, aiming to attract at least 50 participants and 200 spectators, by May 30th, securing sponsorships from at least 3 local businesses and coordinating with the city council for necessary permissions and safety measures. |  |  |

| Resources |  |
| --- | --- |
| Human Resources . On-Site Manager with a certification to install ramps, rails, and half-pipes in a public place; . Manager for relationship with Sponsors; . Manager for relationship with local authorities; . Social Media Manager; . Manager of the volunteers crew. | Budget The estimated cost of 6.000 € is covered by a sum of 2.000 € from each of the 3 Main Sponsors. A fee of 20 € from each participant plus donations of Junior sponsors and spectators will cover the eventual extra expenses or will allow to produce more merchandising |
| Tools and Materials . Ramps, rails, and half-pipes. . Laptop and Internet Connection. . Banners and emergency lights. . Speakers and microphone. . Cleaning Materials and tools. . First Aid Kit | Special needs, Backups and Options Eventual extra expenses will be covered with the funds in the Club Account; Verify the possibility that the municipality will cover the costs for the Site Setup. |

| Risks Safety Concerns and Injuries: Skateboarding, inherently, comes with the risk of injuries. From minor falls to more severe accidents, there's always the possibility that participants might get hurt. Insufficient Participation or Spectator Turnout: the turnout of participants or spectators might not meet expectations. Factors like unfavorable weather, conflicting local events, or even a lack of interest can lead to lower attendance. Financial Shortfalls: Relying heavily on sponsorships and local business support can be risky. There might be instances where the funds procured through sponsorships or entry fees fall short of the actual expenses incurred in organizing the event. Logistic Failures or Delays: Delays in setups, miscommunication among the organizing team, or even external factors like delayed shipments for event materials can disrupt the event schedule. | Deliverables Event Venue Setup: A fully-equipped venue with ramps, rails, and spectator seating. This includes clearly marked zones for activities, signages, and setups for registration, first aid, and refreshment stalls, ensuring a seamless event flow. Marketing Package: A cohesive set of promotional tools: digital ads for social media, posters for local distribution, teaser videos of skateboarding highlights, and an online registration platform to engage potential participants and spectators. Tournament Blueprint: A detailed event schedule outlining segments and timelines. Clear delineations of responsibilities for team members, including contingency plans for emergencies. Post-Event Documentation: A compiled report capturing event statistics, feedback, and financial outcomes. Accompanied by a media kit with event photographs, video summaries, and press materials to share with stakeholders and for future promotional use. |
| --- | --- |
| Costs Venue Costs: This includes fees for booking the local park, any necessary permits, and potential costs associated with modifying the site to fit the event's needs. € 1.200 Equipment and Setup Costs: Investment in skateboarding apparatus such as ramps, rails, and half-pipes. Also, costs for seating arrangements, booths, and other essential infrastructures. € 2.000 Promotional and Marketing Costs: Expenses related to digital marketing, printing posters, producing teaser videos, and other promotional materials. € 800 Operational Costs: Payments for staff or judges, security, first aid facilities, and potentially renting additional amenities like portable toilets or tents. € 900 Logistical Costs: Potential fees for transportation of equipment, catering for participants and volunteers, and any other movement-related expenses. € 700 Post-Event Costs: Expenses for producing a media kit, organizing acknowledgment ceremonies, and any potential cleanup or restoration needed for the venue post-event. € 400 | Metrics (KPI) Number of Partecipants: 50 Number of spectators: 200 Number of Sponsor: 3 Amount raised from Sponsors: 6.000 € Total Expenses: Less than 6.000 € Number of Complains from attendant: 2 |
| Assumptions Interest Level: There's significant local interest in skateboarding, ensuring a sufficient number of participants and spectators. Sponsor Engagement: At least three local businesses will be interested in sponsorship opportunities, providing essential funding. Weather: Favorable weather conditions will prevail on the event day, avoiding cancellations or rescheduling. Venue Availability: The local park will be available and suitable for the event, needing minimal modifications. Team Collaboration: Volunteers and organizing team members will actively collaborate, ensuring efficient task execution. Safety: Provided safety measures will be adequate to prevent or manage potential injuries or incidents. | Constrains Budgetary Limits: With a fixed budget, choices in venue, equipment, and promotional strategies might be restricted, potentially affecting the overall quality. Time Frame: A tight deadline can limit preparation, impacting tasks like securing permissions, attracting sponsors, and effectively marketing the event to potential participants and spectators. Resource Availability: Limited access to necessary equipment, qualified judges, or experienced event personnel can hinder the event's smooth execution and overall success. Permit and Regulatory Restrictions: Local regulations or delays in securing necessary permits can constrain the event's size, location, or the type of setups allowed, imposing structural limitations. |

| KEY Milestones |  |  |  |
| --- | --- | --- | --- |
|  | KICKOFF |  | 15 Apr |
| # | WBS - Activity | Start | End |
| 1 | Venue Preparation and Setup | 16 Apr | 20 May |
|  | Secure the local park as the venue for the tournament. |  |  |
|  | Coordinate with the city council for permits and ensure all safety regulations are met. |  |  |
|  | Set up ramps, rails, and other required skateboard apparatus. |  |  |
|  | Organize interactive sessions or demonstrations during event intervals to keep the spectator's engagement. |  |  |
| 2 | Sponsorship and Collaboration | 16 Apr | 20 May |
|  | Approach at least three local businesses for sponsorship, offering them advertising space at the event. |  |  |
|  | Collaborate with local media outlets for event promotion and coverage. |  |  |
|  | Engage with local skateboard shops or brands for possible partnerships, ensuring mutual promotion and support. |  |  |
| 4 | Event Execution | 30 May | 31 May |
|  | Organize the event in various categories, possibly based on age or skill level, to ensure wide participation. |  |  |
|  | Arrange for experienced judges to evaluate performances. |  |  |
|  | Organize award ceremonies for category winners and provide certificates or medals as tokens of achievement. |  |  |
| 5 | Post-event Activities | 01 Jun | 02 Jun |
|  | Collate feedback from participants, sponsors, and spectators to gauge the event's success and areas of improvement. |  |  |
|  | Publish event highlights and results on local media platforms and social media channels. |  |  |
|  | Organize a small gathering or celebration for the volunteers and key stakeholders to acknowledge their efforts. |  |  |
|  | Closure/Handover Meeting |  | 4 June |

| Giovanni Toccu ___________________ | Feb 02 2023 | Piotr Malarz ___________________ |
| --- | --- | --- |